## Project Planner
Visual Question Answering @ Research & Technical Presentation
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 40 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Find Top 10 Computer Vision Labs | 1 | 2 | 1 | 2 | 100%
Find Newest Publications of CV Labs | 3 | 3 | 3 | 3 | 100%
Look for Available Resources @ Scholar | 6 | 1 | 6 | 1 | 100%
Research Title Definition | 6 | 14 | 6 | 14 | 100%
Crawl Scholar for More Resources on VQA | 20 | 7 | 20 | 7 | 50%
Complete the Prepared Survey on VQA | 25 | 15 | 25 | 14 | 100%
Complete the Second Survey on VQA | 40 | 8 | 40 | 7 | 5%
Sync More Publications on VQA with Mendeley | 48 | 2 | 48 | 2 | 0%
Sort Synced Publications According to Journal/Conference Impact Factor | 50 | 1 | 50 | 1 | 0%
Understand How to Write a Proposal | 51 | 2 | 51 | 2 | 0%
Write a Proposal for Research Title | 53 | 1 | 53 | 1 | 0%
Proposal Improvement | 54 | 2 | 54 | 2 | 0%
Presentation Syllabus Definition | 56 | 1 | 56 | 1 | 0%
Presentation Preparing | 57 | 3 | 57 | 3 | 0%
Learn Latex | 12 | 20 | 12 | 20 | 55%
Get More Information on the Topic from CEIT Professors | 1 | 50 | 1 | 50 | 30%